| TASK | ASSIGNED TO | START | END |
| --- | --- | --- | --- |
| - Update MTFP to reflect National/Regional guidance, emerging issues and strategic direction | Head of Finance (HOF) | 30/06/2025 | 01/08/2025 |
| - Chief Officer Team (COT) briefing on updated MTFP | Chief Finance Officer (CFO CC) | 01/09/2025 | 01/09/2025 |
| - Formal Budget Setting commences in Finance Department (including four-month Precept consultation between October and January) | Finance | 01/09/2025 | 01/09/2025 |
| - Accountability & Assurance Board (AAB) briefing on updated MTFP, planning process, strategic direction and budget setting | CFO CC | 03/09/2025 | 03/09/2025 |
| - OPCC Executive Team briefing on updated MTFP | Chief Finance Officer (CFO OPCC) | 05/09/2025 | 05/09/2025 |
| - Joint Audit Committee (JAC) briefing on MTFP, strategic direction, budget setting timetable | CFO OPCC | 18/09/2025 | 18/09/2025 |
| - Police and Crime Panel (PCP) briefing on MTFP, planning process, strategic direction and budget setting | PCC | 26/09/2025 | 26/09/2025 |
| - Produce initial budget proposal | Finance | 29/09/2025 | 31/10/2025 |
| - COT briefing on updated MTFP and budget proposal formulation | CFO CC | 29/09/2025 | 29/09/2025 |
| - OPCC Executive Team briefing on MTFP | CFO OPCC | 29/09/2025 | 29/09/2025 |
| - Update MTFP to reflect strategic direction following COT/OPCC briefing | HOF | 06/10/2025 | 10/10/2025 |
| - CFO OPCC briefing on MTFP | CFO CC | 06/10/2025 | 10/10/2025 |
| - Precept Pre-Consultation Commences | CFO OPCC | 06/10/2025 | 11/10/2025 |
| - Budget Setting Exercise completed in Finance | Finance & CFO CC | 27/10/2025 | 31/10/2025 |
| - COT briefing on draft Gwent Police Budget Proposal | CFO CC | 03/11/2025 | 07/11/2025 |
| - Chief Constable (CC) finalises Gwent Police Budget Proposal | CFO CC | 03/11/2025 | 07/11/2025 |

| TASK | ASSIGNED TO | START | END |
| --- | --- | --- | --- |
| - CFO OPCC briefing on Gwent Police Budget Proposal | CFO CC | 03/11/2025 | 07/11/2025 |
| - OPCC Strategic Management Board briefing on updated MTFP and consideration of Gwent Police Budget Proposal | CFO OPCC | 12/11/2025 | 12/11/2025 |
| - AAB to consider and discuss Gwent Police Budget Proposal | CFO OPCC / CFO CC | 28/11/2025 | 28/11/2025 |
| - COT briefing on provisional Budget Proposal (post AAB) | CFO CC | 01/12/2025 | 05/12/2025 |
| - JAC Report for circulation with provisional Budget and Precept Proposal | HOF | 26/11/2025 | 26/11/2025 |
| - PCP All-Member Briefing on MTFP and initial budget proposal | CFO OPCC | 28/11/2025 | 28/11/2025 |
| - PCP Report for circulation with provisional Budget and Precept Proposal | CFO OPCC/HOF | 03/12/2025 | 03/12/2025 |
| - JAC briefing on provisional Budget and Precept Proposal | CFO OPCC | 04/12/2025 | 04/12/2025 |
| - PCP briefing on provisional Budget and Precept Proposal | CFO OPCC | 12/12/2025 | 12/12/2025 |
| - Update MTFP to reflect Provisional Settlement and Autumn Statement announcements | HOF | 15/12/2025 | 19/12/2025 |
| - OPCC Planning and Performance Meeting briefing on provisional Budget and Precept Proposal | CFO OPCC | 17/12/2025 | 17/12/2025 |
| - COT briefing on provisional Budget and Precept Proposal | CFO CC | 05/01/2026 | 09/01/2026 |
| - CFO OPCC briefing on provisional Budget and Precept Proposal | CFO CC | 12/01/2026 | 12/01/2026 |
| - Final Police Settlement announced | Home Office / WG | 13/01/2026 | 17/01/2026 |
| - MTFP updated to reflect impact of Final Police Settlement | Finance | 13/01/2026 | 17/01/2026 |
| - OPCC Strategic Management Board Report on PCC Budget and Precept Proposal | CFO OPCC | 16/01/2026 | 26/01/2026 |
| - Deadline for PCC to issue PCP Proposed Precept Report | PCC | 21/01/2026 | 21/01/2026 |
| - PCP Meeting to consider Proposed Precept Report | PCP | 30/01/2026 | 30/01/2026 |

| TASK | ASSIGNED TO | START | END |
| --- | --- | --- | --- |
| - Deadline for PCP to review and report back to PCC on Proposed Precept Report | PCP | 06/02/2026 | 06/02/2026 |
| - Undertake public consultation with non-domestic ratepayers | OPCC | 09/02/2026 | 09/02/2026 |
| - MTFP updated to reflect impact of PCP report | HOF | 10/02/2026 | 10/02/2026 |
| - CFO OPCC briefing on updated MTFP | CFO CC | 11/02/2026 | 11/02/2026 |
| - Draft PCC response to PCP report for circulation | CFO OPCC | 11/02/2026 | 12/02/2026 |
| - Deadline for PCC to issue Revised Precept Proposal Report to PCP | PCC | 13/02/2026 | 13/02/2026 |
| - Deadline for PCP to review Revised Precept Proposal Report and report back to PCC (Second Report) | PCP | 20/02/2026 | 20/02/2026 |
| - Produce Draft Precept Notification | CFO OPCC | 23/02/2026 | 23/02/2026 |
| - Draft PCC response to PCP Second Report for circulation | CFO OPCC | 25/02/2026 | 26/02/2026 |
| - Deadline for PCC to issue response to PCP Second Report | PCC | 27/02/2026 | 27/02/2026 |
| - PCC issues Precept | PCC | 27/02/2026 | 27/02/2026 |
| - Notification of Precept to Local Authorities | CFO OPCC | 27/02/2026 | 27/02/2026 |
| - Produce Final Precept Notification | CFO OPCC | 27/02/2026 | 27/02/2026 |
| - Printing of Precept leaflets / Publishing of on-line Statement (tbc) | Corporate Communications | 02/03/2026 | 06/03/2026 |