## Slide 1: HMICFRS Inspection Progress Report
September 2026
Accountability and Assurance Board
Notes: Subtitle – Arial: Bold. Sentence case. 24 Pt.
Main text – Arial: Reg. Sentence case. 20 Pt.
Bullet Points – Arial: Reg. Sentence case. 20 Pt. Line Spacing 1.5.
Bold where appropriate.
Alternate slide formats between Left & Right.
Do not:
Change text colour.
Enlarge text size.
Move content over background images.

## Slide 2: Area for Improvement 1
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force needs to improve how it records equality data | Chief Superintendent - Head of Continuous Improvement | The force has made progress through governance and development of practical recording guidance. However, the AFI remains open. | A Data Performance Task and Finish Group has been established, chaired at Chief Superintendent level, with representation from Force Contact and Control, Crime Data Integrity, Learning and Development Vulnerability, Equality Diversity and Inclusion and Digital Services Division. National Police Chiefs Council guidance on capturing protected characteristics has been received and is under review. The group has developed short-term solutions around training, policies, operational guidance and performance reviews. | Work is underway to produce clear guidance, including one-page guides, flowcharts, or process maps, supported by Digital Service Division trainers, Learning and Development and Corporate Communications

## Slide 3: Area for Improvement 2
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force should make sure it can effectively monitor and understand the use of force | Chief Superintendent Neighbourhood | The force has made progress through improved data, governance, dip sampling and performance oversight. However, the AFI remains open. | Monthly monitoring is in place through the Coercive Powers meeting, supported by a strengthened performance pack. Use of force data quality has improved significantly. Submission rates for use of force forms have improved, with a clear upward trend over the previous 12 months. Dip sampling is in place with feedback provided to officers. Repeat issues involving officers or supervisors are escalated and tracked. Performance packs now provide greater scrutiny of patterns, trends, disproportionality, age and custody data. | Coercive Powers meeting will continue to oversee steps to improve consistency of supervisory oversight, including BWV review, continue monitoring use of force forms against number of subjects, address self-defined ethnicity recording gaps and ensure safeguarding processes are embedded.

## Slide 4: Area for Improvement 3
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force needs to make sure its external scrutiny panels for stop and search and use of force meet often enough and are representative of the local population | Chief Superintendent Neighbourhood | The force has made progress by developing terms of reference, engaging community leads and piloting a lived-experience scrutiny forum involving young persons. The other independent external scrutiny panel, chaired by the OPCC continues to meet on a quarterly basis and represented by members of the IAG and other individuals where learning is identified and fed back into force. However, the AFI remains open. | Terms of reference have been developed for the external scrutiny panel. Community leads have been engaged, with membership intended to include people with lived experience of police interactions. A pilot panel took place in Pill, Newport in July, with around 25 young people aged 16–22 attending. The OPCC-chaired panel currently meets quarterly, with plans to increase frequency to every two months. | Next steps including confirming ongoing panel dates and frequency, expand the pilot approach across Gwent, ensure membership is representative of local communities, evidence scrutiny impact and organisational learning.

## Slide 5: Area for Improvement 4
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force should make sure its neighbourhood policing model is sustainable to achieve positive long-term solutions to community problems. | Chief Superintendent Neighbourhood | The force has made progress through improved governance, abstraction monitoring and problem-solving support. However, the AFI remains open. | An abstraction policy is in place, with abstractions recorded through Neighbourhood Matters and reported to Engagement Board. The Neighbourhood Strategy is in place. Governance is supported through the Engaged Neighbourhoods monthly meeting which is chaired at Chief Superintendent level. Abstraction monitoring has improved, with hours lost captured and broken down by abstraction type. | The force will continue to monitor abstractions and their impact on capacity and embed the Neighbourhood Policing Guarantee and uplift programme.

## Slide 6: Area for Improvement 5
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force’s systems and management processes need to support effective problem-solving | Chief Superintendent Neighbourhood | The force has made progress through dedicated coordination, training, audits and governance. However, the AFI remains open. | Problem-solving oversight has been strengthened through a dedicated Problem-Oriented Policing (POP) Coordinator, monthly reviews and quarterly Governance and Assurance reviews. POP activity is reported into the Engaged Neighbourhoods meeting, and Neighbourhood Policing Programme (NPP) 2 training has commenced. Problem-solving training is also being delivered to officers, staff and partner agencies. Governance has improved through monthly tracking, audits and senior oversight. | The force will continue to improve consistency in POP plan ownership, reviews and supervisory oversight, continue monthly and quarterly review arrangements and sharing good practice and learning across teams.

## Slide 7: Area for Improvement 6
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force needs to attend calls for service within its published attendance times, effectively supervise incidents and update callers if there are delays. | Chief Superintendent Response | The force has made sustained progress on emergency and priority attendance. However, the AFI remains open. | Attendance at emergency and priority calls has improved and is monitored through daily management meetings, pacesetter meetings and monthly performance packs. Emergency and priority calls are consistently being attended within published timeframes. A Power BI dashboard has been developed to oversee performance. The FCC has been restructured around dispatch, with clearer functional responsibilities. Quality assurance is in place for recontact and reassess, with daily dip sampling and one-to-one feedback. | The force will take steps to improve recontact and reassess compliance, continue work on routine and scheduled call attendance, implement BI metrics for recontact and reassess, reality test the new FCC supervisory model, and continue work to divert demand to online channels.

## Slide 8: Area for Improvement 7
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force needs to make sure that officers and staff assess and report the risk of harm to children and adults thoroughly and promptly. | Chief Superintendent Response | The force has made progress through improved DASH/DARA monitoring, PPN review activity and vulnerability governance. However, the AFI remains open. | Monthly Response performance meetings are in place. DASH/DARA compliance is monitored through vulnerability governance. The force introduced the DARA risk assessment tool in December 2025. PPN submissions are being monitored. A vulnerability lead has been appointed for response teams. | Further work is required to improve data, quality assurance and consistency.

## Slide 9: Area for Improvement 8
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force should make sure it takes all investigative opportunities by creating plans and improving supervision. | Detective Superintendent Investigations and Victims | The force has made progress through revised templates, supervisor training and strengthened governance. However, the AFI remains open. | Work has focused on strengthening investigation planning through the revised Niche template (Investigation Framework 01) and improving supervisory ownership through the Supervisor Update templates 01–03 review framework. Oversight is supported through superintendent-led performance meetings and Investigation Standards governance. The Professionalising Investigations Programme (PIP) 1 supervisor programme is being delivered, and Quality Service Review (QSR) Investigations is in testing phase. | The Quality of Investigations and Victims Change Programme will work to embed SU01–SU03 consistently across teams, monitor compliance through performance meetings, "QSR Investigations" reviews and Investigation Standards Meeting and ensure effective training compliance and performance management at PIP1 and PIP2 level.

## Slide 10: Area for Improvement 9
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force should make sure that it allocates investigations to officers and teams that have both the capability and capacity for timely and thorough investigations | Detective Superintendent Investigations and Victims | The force has made clear progress, particularly through policy review, governance arrangements and workload monitoring. However, the AFI remains open. | The Crime Allocation Policy has been reviewed and is now in place. Daily Management Meeting processes are being used to manage allocation decisions. Workload oversight has also been improved. Officers with more than 15 investigations are being identified for intervention through superintendent-led performance meetings and the Investigation Standards Meeting. Capability is being supported through Learning and Development activity, including PIP1, PIP2 and supervisor training. A PIP policy is being developed to clarify the force position on training, accreditation and retention of staff in core investigative roles. | Progress is being monitored through the Quality of Investigations and Victim Care Change Programme. Further work is required to embed the revised approach and provide assurance that allocation decisions are consistently linked to officer accreditation, experience, workload and capacity.

## Slide 11: Area for Improvement 10
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force must consistently deliver appropriate outcomes for victims. | Detective Superintendent Investigations and Victims | Progress has been made through stronger scrutiny, training and governance, but the AFI remains open. | Outcome performance is embedded in weekly and monthly force and pillar reporting, with the force now reporting on Victim and State based outcomes. Training on appropriate outcomes has been delivered to supervisors and Victim Care staff. | Next steps are to clarify VCOP compliance and set robust performance frameworks to monitor outcomes, open cases and high workloads; and use victim feedback to improve practice.

## Slide 12: Area for Improvement 11
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force should make sure it uses bail and released under investigation effectively to protect victims and prevent interference with investigations | Detective Superintendent Investigations and Victims | The force has made progress through stronger governance, daily scrutiny and policy development. However, the AFI remains open. | Bail and Released Under Investigation governance has improved through daily scrutiny, escalation routes and ongoing policy development. A Bail and RUI policy has been drafted, and interim processes are in place to guide when bail and RUI should be used. A Project Initiation Document has also been submitted to review Bail, RUI and voluntary attendance processes, identify strategic ownership and drive improvement. | Next steps are to finalise and implement the Bail and RUI policy, develop performance reporting and rationalise the strategic ownership of Bail, RUI and VA and ensure these are intrinsically linked with Investigation Standards performance frameworks.

## Slide 13: Area for Improvement 12
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force needs to make sure it complies with national guidance for the Domestic Violence Disclosure Scheme, including meeting disclosure timescales. | Detective Superintendent Public Protection Unit | The force has made significant progress and the AFI is with HMICFRS for review. | The force has made sustained improvement in DVDS performance. Daily monitoring is in place with performance oversight moving into PPU performance meetings. A revised DVDS Standard Operating Procedure has been completed and shared, providing clearer guidance on identity verification and disclosure processes. Additional staffing, revised structures and improved processes have reduced backlog demand and improved service delivery. A dashboard has also been developed to support monitoring of compliance. | Processes are subject to continuous review.

## Slide 14: Area for Improvement 13
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force should increase its use of preventive orders to safeguard vulnerable people in all appropriate cases. | Detective Superintendent Public Protection Unit | The force has made progress through governance, legal engagement and early operational use of Stalking Protection Orders. However, the AFI remains open. | A Protective Orders Working Group was established in April 2026, with monthly meetings attended by Joint Legal Services and operational leads. Work has also started to streamline civil order processes and improve data sharing. | Next steps are to upskill specialist teams on protective order thresholds and processes, improve the quality of order applications, introduce flowcharts and streamlined processes to reduce court delays, and develop and deliver civil orders training. This work will be coordinated and delivered through the Domestic Abuse Protection Orders Implementation Group.

## Slide 15: Area for Improvement 14
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force needs systems which provide reassurance that it takes appropriate action to safeguard adults and children at risk of harm. | Detective Superintendent Public Protection Unit | The force has made progress through recruitment, additional resources, daily monitoring and improved PPN processes. However, the AFI remains open. | Recruitment into safeguarding hub vacancies has been completed, with additional resources aallocated to safeguarding functions. The force has also completed a review of PPN submission and iPatrol processes. Monitoring is now in place for PPNs, strategy discussion compliance and joint visit compliance. It is highlighted that strategy discussion compliance has significantly improved. | Next steps are to improve risk assessment processes and supervisory oversight, continue development of PPN and triage arrangements, include PPN compliance data within performance products, explore technology to assist the research function, and improve consistency of quality assurance. Plans are also being developed with local authority partners to implement governance structures that allow us to scrutinise joint decision making to ensure we are protecting vulnerable people as effectively as possible

## Slide 16: Area for Improvement 15
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force needs to make sure that it has enough suitably trained and skilled staff to effectively carry out its safeguarding roles and functions. | Detective Superintendent Public Protection Unit | The force has made progress through structured training, governance and improved compliance. However, the AFI remains open. | A comprehensive review of safeguarding training requirements has been completed. Introduction to Public Protection and Introduction to Safeguarding Hub training products have been developed and delivered. Training governance is now in place through the Vulnerability Training Steering Group and CID Resourcing meetings. | Next step is to complete skills uplift across specialist safeguarding functions. A review of recruitment into public protection teams is also being undertaken.

## Slide 17: Area for Improvement 16
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force should make sure it understands the factors affecting sickness to improve the well-being of its workforce. | Head of Human Resources | The force has made progress through stronger governance, updated procedures and improving sickness rates. However, the AFI remains open. | A Sickness Improvement Plan and implementation tracker are in place. Updated Police Officer and Police Staff Attendance Management Procedures were published in January 2026. Governance has strengthened through Silver Sickness meetings, People Board oversight, pillar-level sickness meetings, and monthly HR and Occupational Health coordination. | Next steps are to improve sickness data accuracy and analytical capability.

## Slide 18: Area for Improvement 17
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force should make sure it is effectively managing demand and has the right resources, processes and plans in place to keep communities safe. | Chief Superintendent - Head of Continuous Improvement | The force has made progress through demand modelling, benchmarking and operating model review activity. However, the AFI remains open. | Demand modellers have been reviewed to confirm when products were last updated, and response modellers have been re-run. The force is reviewing its modelling cycle to ensure a risk-based approach to understanding demand. Work is also underway through the Operating Model Programme Board, Change Programme and Force Management Statement process. Benchmarking and learning activity has taken place with other forces and through NPCC demand management work. | Further work is required to review Force Management Statement steps 3 and 4.

## Slide 19: Area for Improvement 18
AFI | Owner | Overall Position | Progress Achieved | Next Steps
The force should make sure it effectively communicates organisational change to the workforce. | Chief Superintendent - Head of Continuous Improvement | The force has made progress through improved Employee Opinion Survey (EOS) results, action planning and stronger links between Business Change and Corporate Communications. However, the AFI remains open. | Business Change and Corporate Communications continue to meet regularly, with Change Team input now included in First Line Leaders and Mid Level Leaders courses. All organisational change reviews have a communications strategy or plan. | The next steps are to present the Operating Model Post Implementation Review and Change Toolkit to Service Improvement Board for approval.