| TASK | ASSIGNED TO | START | END |
| --- | --- | --- | --- |
| - Update MTFP to reflect National/Regional guidance, emerging issues and strategic direction | Head of Finance (HOF) | 29/06/2026 | 31/07/2025 |
| - Chief Officer Team (COT) briefing on updated MTFP | Chief Finance Officer (CFO CC) | 01/09/2026 | 01/09/2026 |
| - Formal Budget Setting commences in Finance Department (including four-month Precept consultation between October and January) | Finance | 01/09/2026 | 01/09/2026 |
| - Accountability & Assurance Board (AAB) briefing on updated MTFP, planning process, strategic direction and budget setting | CFO CC | 09/09/2026 | 09/09/2026 |
| - OPCC Executive Team briefing on updated MTFP | Chief Finance Officer (CFO OPCC) | 14/09/2026 | 14/09/2026 |
| - Joint Audit Committee (JAC) briefing on MTFP, strategic direction, budget setting timetable | CFO OPCC | 17/09/2026 | 17/09/2026 |
| - Police and Crime Panel (PCP) briefing on MTFP, planning process, strategic direction and budget setting | PCC | 25/09/2026 | 25/09/2026 |
| - Produce initial budget proposal | Finance | 28/09/2026 | 30/10/2026 |
| - COT briefing on updated MTFP and budget proposal formulation | CFO CC | 28/09/2026 | 28/09/2026 |
| - OPCC Executive Team briefing on MTFP | CFO OPCC | 28/09/2026 | 28/09/2026 |
| - Update MTFP to reflect strategic direction following COT/OPCC briefing | HOF | 05/10/2026 | 09/10/2026 |
| - CFO OPCC briefing on MTFP | CFO CC | 05/10/2026 | 09/10/2026 |
| - Precept Pre-Consultation Commences | CFO OPCC | 05/10/2026 | 09/10/2026 |
| - Budget Setting Exercise completed in Finance | Finance & CFO CC | 26/10/2026 | 30/10/2026 |
| - COT briefing on draft Gwent Police Budget Requirement | CFO CC | 02/11/2026 | 06/11/2026 |
| - Chief Constable (CC) finalises Gwent Police Budget Requirement | CFO CC | 02/11/2026 | 06/11/2026 |

| TASK | ASSIGNED TO | START | END |
| --- | --- | --- | --- |
| - CFO OPCC briefing on Gwent Police Budget Requirement | CFO CC | 02/11/2026 | 06/11/2026 |
| - OPCC Strategic Management Board briefing on updated MTFP and consideration of Gwent Police Budget Proposal | CFO OPCC | 06/11/2026 | 06/11/2026 |
| - JAC Report for circulation on MTFP and Gwent Police Budget Proposal | HOF | 25/11/2026 | 25/11/2026 |
| - AAB to consider and discuss Gwent Police Budget Requirement | CFO OPCC / CFO CC | 26/11/2026 | 26/11/2026 |
| - COT briefing on Gwent Police Budget Proposal (post AAB feedback) | CFO CC | 30/11/2026 | 04/12/2026 |
| - PCP Report for circulation on MTFP and Gwent Police Budget Proposal | CFO OPCC/HOF | 02/12/2026 | 02/12/2026 |
| - JAC briefing on MTFP and Gwent Police Budget Proposal | CFO OPCC | 03/12/2026 | 03/12/2026 |
| - PCP All-Member Seminar on MTFP and Gwent Police Budget Proposal | CFO OPCC | 04/12/2026 | 04/12/2026 |
| - PCP briefing on MTFP and Gwent Police Budget Proposal | CFO OPCC | 11/12/2026 | 11/12/2026 |
| - Update MTFP to reflect Provisional Settlement and Autumn Statement announcements | HOF | 14/12/2026 | 18/12/2026 |
| - OPCC Executive Team discussion on Budget Requirement and Precept Proposal | CFO OPCC | 14/12/2026 | 21/12/2026 |
| - OPCC Planning and Performance Meeting briefing on Budget Requirement and Precept Proposal | CFO OPCC | 17/12/2026 | 17/12/2026 |
| - COT briefing on Budget Requirement and Precept Proposal | CFO CC | 04/01/2027 | 08/01/2027 |
| - CFO OPCC briefing on Budget Requirement and Precept Proposal | CFO CC | 11/01/2027 | 11/01/2027 |
| - OPCC Strategic Management Board Report on PCC Budget Requirement and Precept Proposal | CFO OPCC | 14/01/2027 | 14/01/2027 |
| - Final Police Settlement announced | Home Office / WG | 18/01/2027 | 22/01/2027 |
| - MTFP updated to reflect impact of Final Police Settlement | Finance | 18/01/2027 | 22/01/2027 |
| - Deadline for PCC to issue Budget Requirement and Precept Proposal Report | PCC | 20/01/2027 | 20/01/2027 |
| - PCP All-Member Seminar on Budget Requirement and Precept Proposal Report | CFO OPCC | 22/01/2027 | 22/01/2027 |
| - PCP Meeting to consider Budget Requirement and Precept Proposal Report | PCP | 29/01/2027 | 29/01/2027 |

| TASK | ASSIGNED TO | START | END |
| --- | --- | --- | --- |
| - Deadline for PCP to review and report back to PCC on Budget Requirement and Precept Proposal Report | PCP | 08/02/2027 | 08/02/2027 |
| - Undertake public consultation with non-domestic ratepayers | OPCC | 09/02/2027 | 12/02/2027 |
| - MTFP updated to reflect impact of PCP report | HOF | 09/02/2027 | 09/02/2027 |
| - CFO OPCC briefing on updated MTFP | CFO CC | 10/02/2027 | 10/02/2027 |
| - Draft PCC response to PCP report for circulation | CFO OPCC | 11/02/2027 | 12/02/2027 |
| - Deadline for PCC to issue Revised Budget Requirement and Precept Proposal Report to PCP | PCC | 15/02/2027 | 15/02/2027 |
| - Deadline for PCP to review Revised Budget Requirement and Precept Proposal Report and report back to PCC (Second Report) | PCP | 22/02/2027 | 22/02/2027 |
| - Produce Draft Precept Notification | CFO OPCC | 24/02/2027 | 24/02/2027 |
| - Draft PCC response to PCP Second Report for circulation | CFO OPCC | 25/02/2027 | 26/02/2028 |
| - Deadline for PCC to issue response to PCP Second Report | PCC | 01/03/2027 | 01/03/2027 |
| - PCC issues Precept | PCC | 01/03/2027 | 01/03/2027 |
| - Notification of Precept to Local Authorities | CFO OPCC | 01/03/2027 | 01/03/2027 |
| - Produce Final Precept Notification | CFO OPCC | 01/03/2027 | 01/03/2027 |
| - Printing of Precept leaflets / Publishing of on-line Statement (tbc) | Corporate Communications | 02/03/2027 | 06/03/2027 |